## product backlog
Title/User Story | Description/Activity | Prio (1 = high) | Status | Start Date | Est Time (weeks or days) | Estimated Time S/M/L (1d/2d/3d) | Days | Actual Time | Planned Sprint | Comment
Record | Record sounds with the device microphone. | 1 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | Limitation at 1 minute. Notification if you leave the record.
Record sources | the user will be able to record from the internal or an external microphone | 3 | Ongoing | 30/12/13 | 0,5 | s | 0,5 |  |  | none
Buffer Record | Temporarely store the audio | 2 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | find the best way to store audio during record
save record | save the file in the default folder | 3 | Ongoing | 30/12/13 | 0,5 | s | 0,5 | 0 |  | none
Interface | Multi-device layout (tablet 7 inch and mobile phone) | 1 | Ongoing | 30/12/13 | 3 | l | 3 | 0 | x | Easy access to basic functions. 3 layouts.
Manage / storage | Store the record on the SD card. You can choose where and different format. | 1 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | Store the file in different formats, rename it, delete it and choose where you want store it.
Play | send the audio to an external media player | 3 | Ongoing | 30/12/13 | 0,5 | s | 0,5 |  |  | we can use an external player for play, pause and stop to listening the file
Share | The record file can be share with another device. | 1 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | The file can be send by mail, Bluetooth….
Settings | Change the default file storage, and the format | 3 | Ongoing | 30/12/13 | 1 | s | 1 | 0 |  | Interface to easily change every settings

## Sprint backlog
Title/User Story | Description/Activity | Priority (1 = high) | System | Estimated Time (day) | Started | estimated time (S/M/L) | Developer | Status | Comment
Plan the meal | Invite others user to join the meal | 1 | Application | 2 | 29/04 | M | Manu/yuguo | Ongoing | Create a form and send it. Receive confirmations and invitations
Backend | Manage user info | 1 | Backend | 2 | 27/04 | S | Yann | Done | none
Online reservation | make a reservation and order meal online | 1 | Application /backend | 1 | x | M | Manu/yuguo | Ongoing | Create a form and send it.
Offline reservation | make a reservation and order meal offline, peering | 1 | Application | 1 | x | M | Manu/yuguo | Ongoing | Prestetting form and send it, Nfc for peering
Line up offline | Nfc tag and communication with backend | 1 | Application /backend | 1 | x | M | Robin / Yann | Ongoing | Nfc communication / manage line on the bakend
Settings | Set parameters for android application and some filters | 2 | Application | 2 | X | L | Robin | Ongoing | general settings and filters
Push service | Receive push for the application and send it for the backend | 1 | Application /backend | 1 | X | S | Robin / Yann | Ongoing | Use google service for push notification
Manage seat and meal | check reservation, manage meal | 1 | Webapp /backend | 2 | X | M | Guillaume /seven | Ongoing | none
Manage the line up | send push when the table is ready | 1 | Webapp /backend | 1 | X | M | Guillaume /seven | Ongoing | none